Source	MARKET NEWS

Date	02/21/2017

Time	08:34:00 AM

Company	 Anfield Gold Corp.

Title	Progress

Update On The Coringa Project

CDNX Symbol: ANF

Press Release

ANFIELD GOLD CORP ("ANF-V")

- Progress Update On The Coringa Project

Anfield Gold Corp. ("Anfield" or the "Company") is pleased to

report on progress at its 100% owned Coringa Gold Project (the

"Project") in Para State, Brazil.

The Company has made significant progress towards the goal of

advancing the Project into production. The disassembly and relocation

of the Andorinhas Plant purchased from Troy Resources has been

completed. The majority of the plant and mining equipment has been

moved to the Project. Major plant components such as crushers,

compressors, ball mills and mining equipment have been refurbished and

are ready for installation. A detailed CIL plant design for

construction is well advanced, and the tailings storage facility final

design is near completion. Procurement of long lead time and critical

components of the plant has been initiated.

In support of this work and towards completion of the Project

feasibility study, site characterization, metallurgical, geotechnical,

hydrogeologic and condemnation drilling has been completed. In

addition, site infrastructure and ancillary facility construction is

well advanced including: construction of project camp, office and

maintenance facilities, upgrading and improvement of Project access

roads including construction of storm water control structures.

The 20,000 metre infill drilling program has been expanded to

approximately 26,500 metres and, to date, the Company has completed

23,417m of this drilling. The infill drilling program is expected to be

completed in March and results will be used to finalize the feasibility

study resource model, mine design and schedule. The company has also

completed other types of drilling at the project in support of the

feasibility study and these are summarized in Table 1.

//st

Drilling Purpose       Number of      Diamond    Reverse-

drill holes  Drill Holes Circulation

(m)   Holes (m)

Infill Resource Drilling     154       15,207      8,210

Geotechnical Drilling         24        1,491          -

Condemnation Drilling          4          743          -

Water Well Drilling           14            -        617

Metallurgical sampling

drilling                      4          285          -

TOTAL                        186       18,343          -

Table 1. Breakdown of

Anfield's drilling

at the Project by purpose.

//et

The Company expects to complete the Project feasibility study in

the second quarter of 2017. Geology, engineering, environmental and

social studies supporting the study are ongoing. Reassembly of the

plant and mine development at the Project will begin once detailed

engineering is complete and the required permits are obtained.

The Company has applied for trial mining licenses to allow for

initial construction and installation of the plant at the Project,

underground mine development, pilot scale mining and the sale of gold,

and expects to receive the licenses shortly. In addition, permitting

efforts are ongoing to obtain the mining concession license and related

operating licenses for the Project. These will allow for the planned

full scale production rate of 750 tonnes of mineral reserve per day.

Anfield Gold Corp.

Marshall Koval, Chairman & CEO

Neither the TSX Venture Exchange nor its Regulation Services

Provider (as that term is defined in the policies of the TSX Venture

Exchange) accepts responsibility for the adequacy or accuracy of this

news release.

The foregoing information contains forward-looking statements

regarding Anfield's future plans. In making the forward-looking

statements in this release, Anfield has applied certain factors and

assumptions that are based on information currently available to

Anfield as well as Anfield's current beliefs and assumptions. Although

Anfield considers these beliefs and assumptions to be reasonable based

on information currently available to it, they may prove to be

incorrect, and the forward-looking statements in this release are

subject to numerous risks, uncertainties and other factors that may

cause future results to differ materially from those expressed or

implied in such forward-looking statements. Such risk factors include,

among others, risks associated with the business of Anfield, risks

related to reliance on technical information provided by Magellan

Minerals Ltd. as related to the Coringa project; risks relating to

exploration and potential development of Magellan Minerals Ltd.'s

projects; risks related to obtaining the permits and approvals

necessary to develop and commission the Coringa project on terms that

are acceptable to Anfield; risks related to Anfield identifying

suitable acquisition targets; business and economic conditions in the

mining industry generally; the supply and demand for labour and other

project inputs; prices for commodities to be produced and changes in

commodity prices; changes in interest and currency exchange rates;

risks relating to inaccurate geological and engineering assumptions

(including with respect to the tonnage, grade and recoverability of

reserves and resources); risks relating to unanticipated operational

difficulties (including failure of plant, equipment or processes to

operate in accordance with specifications or expectations, cost

escalation, unavailability of materials and equipment, government

action or delays in the receipt of government approvals, industrial

disturbances or other job action, and unanticipated events related to

health, safety and environmental matters); risks relating to adverse

weather conditions; political risk and social unrest; changes in

general economic conditions or conditions in the financial markets; and

changes to business and economic conditions in the mining industry

generally. Although Anfield has attempted to identify important factors

that could cause actual results to differ materially from those

contained in forward-looking information, there may be other factors

that cause results not to be as anticipated, estimated or intended.

There can be no assurance that such information will prove to be

accurate, as actual results and future events could differ materially

from those anticipated in such statements. Accordingly, readers should

not place undue reliance on forward-looking information. Anfield does

not undertake to update any forward-looking information, except in

accordance with applicable securities laws.

Contact Information:

Anfield Gold Corp.

Martin Rip

+ 604 646-1884

+ 604 687-7041 (FAX)

______________________________

_______________________________________________

TSX Venture closing price for ANF-V

Date: 2017/02/17

Closing Price: 1.14

____________________________________________________________

(c)2017 Market News Publishing Inc.  All rights reserved.

Toronto:(416)366-8881   Vancouver:(604)689-1101   Fax:(604)689-1106

#1705100035TS11705101469-08321320170221##