Source	MARKET NEWS

Date	08/29/2018

Time	05:59:40 AM

Company	 Alphamin Resources Corp.

Title	Project

Update, Releases Interim Results

CDNX Symbol: AFM

Press Release

ALPHAMIN RESOURCES CORP ("AFM-V;AFMJF-0")

- Project Update, Releases Interim Results

Alphamin Resources Corp. ("Alphamin" or the "Company") is pleased

to announce an update on progress at its Bisie Tin Project.

Construction of the Company's 80.75% owned Bisie Tin Project is

currently on schedule and 75% complete. Commissioning of the process

plant is scheduled for Q1 2019. Equity financing raised to date

together with the US$80m credit facility is currently projected to take

the Company through to commercial production.

Key project highlights include:

//st

Safety                      Over 1 million-man hours worked by over

600 employees with no lost time injuries

reported.

Mine construction           Progressing ahead of schedule with 1709

development meters complete out of a

total of 2,700.

Process plant               Construction ahead of schedule with 256

tons of steel erected with majority of

kit required now on site.

Infrastructure              Construction of the Company's 36Km access

road to site and airstrip is now complete

with project deliveries getting through

to site without difficulty.

Logistics and procurement   73% of project loads have been delivered

to the mine site. Procurement is 90%

complete.

Social and community        Social development investments targeting

over 1500 households for livelihoods and

community infrastructure projects

continue. Site security and community

relations have been strengthened further

by the peaceful and voluntary migration

of the remaining 500 artisanal miners

from Alphamin's concession in late 2017

and early 2018.

//et

The recent Ebola outbreak in the North Kivu province is being

monitored closely and strict protocols have been put in place to reduce

the risk of transmission at Bisie. The outbreak is located some 1,200km

from Bisie by road. To date there has been no impact on the Company's

operations.

The Company has also filed its interim financial statements for

the three and six months ended June 30, 2018 and Management Discussion

and Analysis - quarterly highlights, which are available on SEDAR.com.

Further information, videos and photographs of the Project's

progress are available on the Alphamin Resources Corp. website at

www.alphaminresources.com

EDITORS NOTES:

FOR MORE INFORMATION, PLEASE

Contact Information:

CONTACT:

//st

Boris Kamstra             Alphamin Resources Corp.

Chief Executive Officer   Tel: +230 269 4166

E-mail: boris.kamstra@alphaminresources.com

//et

Neither the TSX Venture Exchange nor its regulation services

provider (as that term is defined in the policies of the TSX Venture

Exchange) accepts responsibility for the adequacy or accuracy of this

News Release.

ISSUED ON BEHALF OF THE BOARD OF DIRECTORS OF ALPHAMIN RESOURCES

CORP. BY: Boris Kamstra, Chief Executive Officer Tel: +230 269 4166

Grand Baie, Mauritius

CAUTION REGARDING FORWARD LOOKING STATEMENTS

Information in this news release that is not a statement of

historical fact constitutes forward-looking information.

Forward-looking statements contained herein include, without

limitation, statements relating to the intended completion of

additional financing and the anticipated use of funds from such

financing, the participation of Tremont and other stakeholders, the

satisfaction of conditions precedent under the Credit Facility, the

Company's intentions to raise the balance of funding required to

complete construction of the Project and the sources thereof,

additional subscription by IDC, costs of production, success of mining

operations, the ranking of the project in terms of cash cost and

production, economic return estimates, social, community and

environmental impacts, and continued positive discussions and

relationships with local communities and stakeholders. Forward-looking

statements are based on assumptions management believes to be

reasonable at the time such statements are made. There can be no

assurance that such statements will prove to be accurate, as actual

results and future events could differ materially from those

anticipated in such statements. Accordingly, readers should not place

undue reliance on forward-looking statements. Although Alphamin has

attempted to identify important factors that could cause actual results

to differ materially from those contained in forward-looking

statements, there may be other factors that cause results not to be as

anticipated, estimated or intended. Factors that may cause actual

results to differ materially from expected results described in

forward-looking statements include, but are not limited to: Alphamin's

ability to secure sufficient financing to advance and complete the

Project, uncertainties associated with Alphamin's resource and reserve

estimates, uncertainties regarding the estimation of future costs,

uncertainties regarding global supply and demand for tin and market and

sales prices, uncertainties associated with securing off-take

agreements and customer contracts, uncertainties with respect to

social, community and environmental impacts, adverse political events,

uncertainties with respect to optimization opportunities for the

Project, as well as those risk factors set out in the Company's

Management Discussion and Analysis and other disclosure documents

available under the Company's profile at www.sedar.com. Forward-looking

statements contained herein are made as of the date of this news

release and Alphamin disclaims any obligation to update any

forward-looking statements, whether as a result of new information,

future events or results or otherwise, except as required by applicable

securities laws.

____________________________________________________________

(c)2018 Market News Publishing Inc.  All rights reserved.

Toronto:(416)366-8881   Vancouver:(604)689-1101   Fax:(604)689-1106

#1824000027TS11824000779-05580620180829##