Source	MARKET NEWS
Date	06/29/2017
Time	09:54:12 AM

Company	 Hudson Resources Inc.
Title	Update on 
Engineering and Construction Activitie





    CDNX Symbol: HUD











Press Release





HUDSON RESOURCES INC ("HUD-V;HUDRF-0")
- Update on Engineering and Construction Activities at the White
- Mountain Anorthosite Project in Greenland

HUDSON RESOURCES INC. (the "Company") is pleased to provide an
update on engineering and construction activities at the company's
White Mountain Anorthosite project in western Greenland. So far this
year, activities have focused on completing the civil works in the
field, finalizing detailed engineering, and the procurement of all of
the major project components for the process plant and
infrastructure.(br/)

With respect to civil works, RTS Greenland A/S, is currently
finishing the drill and blast operations to prepare for foundations for
the process plant, product storage building and ancillary
infrastructure.

Civil works will continue through to the fall to support the
project infrastructure. Concrete foundation work will commence shortly
upon finalization of an agreement with a contractor. Building erection
and mechanical installation are planned to commence in the fall.

With regard to engineering, CWA Engineers Inc. have completed all
but a few remaining detailed engineering drawings.  Hudson has also
engaged Ramboll Group A/S and Automatic Syd A/S, both out of Denmark,
for the electrical engineering and motor control center (MCC)
facilities.

Major on site accomplishments so far this year include:

*  Completion of a new access road from the port;
*  Completion of blasting for the warehouse, which is a 90m by 45m

building for storing 30,000 tonnes of final product;
*  Completion of the access roads for the bollards at the dock;
*  Completion of the process plant site which is a 40m by 40m pad;

*  Preparation of the site for the accommodation complex; and
*  Receipt of materials for preparation of the concrete foundation

work.

"We are very pleased to be undertaking these activities on site as
we advance the project towards commercial production," commented James
Tuer, Hudson's president. "This next phase in our company's history is
to transform from explorer to producer and bring a unique resource to
market. We believe this will generate a number of exciting new business
lines for the company including supplying feed product to the E-Glass
fiberglass market, the paints and coatings business and the alumina
industry."

"Construction activities are proceeding well; however, a late
revision in the process plant design will result in the delayed
delivery of some of the conveyors. This, along with a few other delays,
will push our ambitious goal of commissioning the plant by late 2017 to
the middle of next year when we expect to commence shipping product. In
the meantime, potential customers continue to test our anorthosite for
E-Glass and coatings applications with positive results and Hudson is
working towards additional off-take agreements."

Procurement of all major project components is now complete.  The
following have now been purchased and are expected to be ready for
shipment over the next couple of months:

*  Product storage building and Process building (Norsteel
Buildings);
*  Truck maintenance building (Vertical Building Structures);
*  Maxtrak 1000 SR Mobile cone crusher to feed the plant
(Powerscreen);
*  Two High Pressure Grinding Rolls installed in the plant (Weir
Minerals);
*  Six high intensity magnetic separators (Eriez Manufacturing);
*  Three coarse and two quad deck fine screens for sorting product

(Derrick Corporation);
*  Twenty-three process conveyors (Continental Conveyor - a number
of
which will be delayed)
*  1,200 stph shiploader and conveying system from the warehouse
(Thor
Global);
*  Five 100,000 litre fuel tanks for the fuel farm (CGH Nordic);
*  Used 44 bed accommodation complex (subject to Greenland
government
approval);
*  Various mobile equipment including a 35-tonne and two 90-tonne
cranes, Telehandler, 30-tonne excavator, trucks and concrete
batch
plant; and
*  The 300' by 100' barge that will deliver a significant portion
of
the equipment sourced in North America and then be moored as
the
floating wharf this fall.

Hudson owns 100 percent of the White Mountain project. The company
was granted a 50-year mining license in 2016, and the deposit has
resources defined for more than 100 years of production. Hudson will
provide photos of the construction progress on a regular basis on its
website.

ON BEHALF OF THE BOARD OF DIRECTORS

"James Tuer"
James Tuer, President

Forward-Looking Statements(br/)

This news release includes certain forward-looking statements or
information.  All statements other than statements of historical fact
included in this news release, including, without limitation,
statements regarding the use of proceeds from the private placement,
and other future plans and objectives of the Company are
forward-looking statements that involve various risks and
uncertainties.  There can be no assurance that such statements will
prove to be accurate and actual results and future events could differ
materially from those anticipated in such statements. Important factors
that could cause actual results to differ materially from the Company's
plans or expectations include market prices, general economic, market
or business conditions, regulatory changes, timeliness of government or
regulatory approvals and other risks detailed herein and from time to
time in the filings made by the Company with securities regulators. The
Company expressly disclaims any intention or obligation to update or
revise any forward-looking statements whether as a result of new
information, future events or otherwise except as otherwise required by
applicable securities legislation.

Neither the TSX Venture Exchange nor its Regulation Services
Provider (as that term is defined in the policies of the TSX Venture
Exchange) accepts responsibility for the adequacy or accuracy of this
release.

For further information:
James Tuer, President
Ph: 604-628-5002 or 604-688-3415
























TSX Venture closing price for HUD-V
Date: 2017/06/28
Closing Price: 0.47

TEL: 604-628-5002    HUDSON RESOURCES INC
FAX: 604-688-3452
E-mail: info@hudsonresources.ca
Website: www.hudsonresources.ca
____________________________________________________________
(c)2017 Market News Publishing Inc.  All rights reserved.
Toronto:(416)366-8881   Vancouver:(604)689-1101   Fax:(604)689-1106

1717900036TS11717901886-09502320170629