Source	MARKET NEWS
Date	05/31/2016
Time	09:56:19 AM

Company	 Red Eagle Mining Corporation
Title	Continues 
to Advance Construction of the San Ram





    CDNX Symbol: RD











Press Release





RED EAGLE MINING CORP ("RD-V")
- Continues to Advance Construction of the San Ramon Gold Mine
- During Q1 2016

Red Eagle Mining Corporation is pleased to announce financial
results for the three months ending March 31, 2016 and business
highlights to date, including advancements at Red Eagle Mining's San
Ramon Gold Mine in Antioquia, Colombia.

Development and Construction of the San Ramon Gold Mine and Mill

The overall project is approximately 70% complete (based on
physical completion), with earthworks, concrete, platework, steelwork
and mechanical equipment installation on schedule for 100% practical
completion in July 2016. Piping, electrical and instrumentation
installation would continue to completion during Q3 2016.

Project highlights include:

EPCM

Detailed engineering, drawings, and all 3D models for all
structures are complete. The quantities and scope for unit rate
construction contracts have been defined and awarded. The quantities,
scope and prices achieved to date are all within budget. The EPCM
contract has now shifted in focus to "CM" - construction management.

Earthworks

Bulk earthworks were largely completed by the end of 2015,
allowing critical concrete foundations to be poured prior to the close
of the year. All cut slopes have been hydro-seeded with natural grasses
to mitigate environmental impact. All earthworks and grass
hydro-seeding was complete, apart from the dry tailings and mine waste
rock management facility; the construction of which is still
proceeding.

Concrete

All critical concrete foundations were completed before the end of
2015. All major concrete foundations have been completed, and concrete
works are approximately 90% complete.

Procurement and Logistics

By November 2015, Red Eagle Mining had placed all process and
infrastructure equipment orders necessary to complete construction of
the San Ramon Gold Mine and Mill. Deliveries of equipment commenced in
January 2016 and by March 31, 2016, deliveries for the majority of all
major equipment to site were complete.

Structural Steel and Field Erected Tanks

Structural steel fabrication is well advanced and field erected
tanks are fabricated and delivered to site and erection is in progress.
Welding and erection of major tanks are 100% complete, short of
paintwork.

Mechanical Piping, Platework, and Electrical Instrumentation

Mechanical platework fabrication is in progress. Major bins and
chutes have been delivered to site. Mechanical installation is in
progress with the main focus on the SAG mill and Filter presses
installation. Electrical bulk procurement is progressing well. The vast
majority of all instruments have been fabricated and are being shipped
to site. The SAG mill is approximately 90% complete, and the filter
presses are approximately 75% complete, with all components on site.

Underground Mine Development

The underground decline has been collared and tunneling activities
are ongoing. Initial ground conditions are as predicted - weak
weathered granodiorite (saprolite), requiring conventional steel
support and shotcrete. The decline development is in line with the
processing facility and infrastructure schedules to achieve production
during the second half of 2016. Additionally, detailed ore production
stope delineation drilling has commenced, in preparation for this
schedule.

Community Relations and Corporate Social Responsibility ("CSR")

Red Eagle Mining continues to maintain positive relationships with
and be involved with the local communities, keeping them informed of
the advances during the construction of the mine, as well as its
environmental and CSR related activities. To date, Red Eagle Mining has
consistently received positive reception and support from local
communities and stakeholders on the project.

Environmental Progress

Red Eagle Mining has strictly adhered to the terms of its
Environmental License, and the associated Environmental Management Plan
has been followed diligently - inspections and reports to date have all
been positive and in good order.

Red Eagle Mining expects to achieve the upcoming major development
and construction milestones:

* SAG mill and filter presses installation completed in June 2016;


* All mechanical platework installation completed in June 2016;

* Pre-commissioning to commence in Q3 2016;

* Mine and mill construction completion in Q3 2016;

* First gold pour to occur in the second half of 2016; and

* Commercial production by the end of 2016

Project Financing

Based upon Red Eagle Mining's projections and estimated
construction progress made as at April 30, 2016, the construction of
Red Eagle Mining's 100% owned San Ramon Gold Mine and Mill is forecast
to be funded through to full production. As at April 30, 2016, Red
Eagle Mining had approximately US $25 million in cash, and has up to US
$15 million available under the credit facility with approximately US
$29 million of project costs left to incur.

Selected financial data

The following selected financial data is derived from our
unaudited interim condensed consolidated financial statements for the
three months ended March 31, 2016, as prepared in accordance with
International Financial Reporting Standards (all amounts in CA$).

//st
For the three months ended         March 31, 2016 March 31, 2015
Net Loss                                $ 198,822    $ 2,805,754
Comprehensive Loss                        312,283      2,795,075
Basic and Diluted Loss per Share             0.00           0.04

As at March 31,   December 31,
2016           2015
Cash and cash equivalents            $ 28,617,808   $ 10,347,916
Total Assets                          101,438,067     62,582,686
Total Liabilities                      71,048,959     33,573,430
Shareholders' equity                   30,389,108     29,009,256
//et

For the three months ended March 31, 2016, Red Eagle Mining
reported a net loss of $0.2 million (2015: $2.8 million). The net loss
was reduced compared to the 2015 period as Red Eagle Mining commenced
capitalization of direct costs associated with the development of the
San Ramon Gold Mine and also from a higher foreign exchange gain. The
increase in Total Liabilities primarily relates to amounts outstanding
on the construction credit facility.

This press release should be read in conjunction with the
unaudited interim condensed consolidated financial statements and
Management's Discussion and Analysis for the three months ended March
31, 2016. These documents can be found on Red Eagle Mining's website or
profile at www.sedar.com.

The technical information contained in this news release has been
reviewed and approved by Red Eagle Mining's Vice President of
Exploration, Jeff Toohey P.Eng., who is a Qualified Person as defined
under NI 43-101.

General Counsel Appointment

Effective June 6, 2016, Mischa Zajtmann will beappointed as Vice
President & General Counsel of Red Eagle Mining. He began his career as
an associate in the securities and business law group of Blake, Cassels
& Graydon LLP where he gained significant experience with respect to
public companies, capital markets, securities laws and the natural
resources sector. In 2013, Mr. Zajtmann joined Oxygen Capital, as
General Counsel and was responsible for all legal matters affecting
Oxygen and its portfolio entities, which include True Gold, Pilot Gold,
and Pure Gold. Mr. Zajtmann obtained his LLB from the University of
Saskatchewan in 2008 and is called to the bar in both B.C. and Alberta.


Mr. Zajtmann replaces Matthew Howorth whom the Board of Directors
wishes well in his future endeavours.

About Red Eagle Mining

Red Eagle Mining is a well-financed gold exploration and
development corporation with an experienced mine development team.
Management is focused on building shareholder value through discovering
and developing gold projects with low costs and low technical risks in
Colombia, a jurisdiction with prolific historic production but until
recently limited modern exploration. Red Eagle Mining owns 71% of the
Vetas Gold Project and 100% of the Santa Rosa Gold Project, where
construction is underway at the fully permitted and fully financed San
Ramon Gold Mine with production expected to commence in the second half
of 2016.

Neither the TSX Venture Exchange nor its Regulation Services
Provider (as that term is defined in the policies of the TSX Venture
Exchange) accepts responsibility for the adequacy or accuracy of this
release. This news release includes forward-looking statements that are
subject to risks and uncertainties. All statements within, other than
statements of historical fact, are to be considered forward looking.
Although Red Eagle Mining believes the expectations expressed in such
forward-looking statements are based on reasonable assumptions, such
statements are not guarantees of future performance and actual results
or developments may differ materially from those in forward-looking
statements. Factors that could cause actual results to differ
materially from those in forward-looking statements include market
prices, exploitation and exploration successes, continued availability
of capital and financing, and general economic, market or business
conditions. There can be no assurances that such statements will prove
accurate and, therefore, readers are advised to rely on their own
evaluation of such uncertainties. We do not assume any obligation to
update any forward-looking statements. This news release does not
constitute an offer to sell or a solicitation of an offer to sell any
securities in the United States. The securities have not been and will
not be registered under the United States Securities Act of 1933, as
amended (the "U.S. Securities Act") or any state securities laws and
may not be offered or sold within the United States or to U.S. Persons
unless registered under the U.S. Securities Act and applicable state
securities laws or an exemption from such registration is available.

SOURCE Red Eagle Mining Corporation
______________________________________
_______________________________________________
TSX Venture closing price for RD-V
Date: 2016/05/30
Closing Price: 0.61
____________________________________________________________
(c)2016 Market News Publishing Inc.  All rights reserved.
Toronto:(416)366-8881   Vancouver:(604)689-1101   Fax:(604)689-1106

1615100040TS11615101710-09551020160531