Source	MARKET NEWS

Date	05/24/2018

Time	05:26:32 AM

Company	 Victoria Gold Corp.

Title	Provides

Eagle Development Update, Yukon Territo

CDNX Symbol: VIT

Press Release

VICTORIA GOLD CORP ("VIT-V;VITFF-0")

- Provides Eagle Development Update, Yukon Territory

Victoria Gold Corp. "Victoria" or the "Company" is pleased to

provide a construction update for the Eagle Gold Mine Project (the

"Project"), Yukon Canada. Full construction commenced March 15, 2018

with completion and first gold pour scheduled for the second half of

2019.

"The successful construction program completed late in 2017

allowed us to hit the ground running and construction of the Eagle Gold

Mine is off to an outstanding start," stated John McConnell, President

& CEO. "I am pleased with the significant number of Yukon based

companies and Yukon First Nation partnered businesses that have already

been engaged for construction which has resulted in a high level of

local hiring. This is an important focus area for Victoria as we build

Yukon's next and largest ever gold mine."

Engineering

Significant ramp up of engineering activities occurred during

March and April with overall engineering now at approximately 65%

complete. Currently, engineering activities are focused on Issued For

Construction ("IFC") drawings for concrete site works, power

transmission and schedule driven deliverables based on fabrication and

equipment delivery schedules.

Procurement

Total Project commitments to date are nearly C$200 million with

C$55 million incurred cost.  The 2016 Feasibility Study construction

capital plus year one sustaining capital was estimated at C$411

million, and the revised construction capital estimate was finalized at

C$442 million. The decision to purchase all new, as opposed to used,

major mobile equipment (to improve operational efficiency and take

advantage of attractive pricing) as well as inflationary increases in

pricing across the Project were main drivers for this capital increase.

All major long lead items have been procured, materially reducing the

risk of schedule delays for construction completion toward first gold

pour. All primary mobile mining equipment is scheduled to arrive at

site in June 2018 with crushers to follow in the Fall of this year.

Site Construction

Major earthworks are well underway on site and are focused on the

crushing plant, gold recovery plant and heap leach facility

preparation. Concrete contracts have been awarded and casting of

foundations for the crushing and gold recovery facilities will start

this July. Camp expansion from 250 to full 450 bed capacity has been

on-going and is scheduled for completion by the end of this month.

Total on-site construction work to date exceeds 185,000 hours. A

strong health, safety and environmental program and culture have been

established at site as witnessed by no lost time accidents.

Recruitment

Victoria continues to recruit senior staff for the owner's team as

operational readiness planning develops. This month, the Company

welcomes staff to the environmental and site support team with a

continued focus on hiring Yukoners.

Permitting

Pursuant to the Company's Water License, Victoria is required to

submit a number of post licensing submissions for Review and Approval

as a condition of license. Earlier this year, the Company made

submission of the revised heap leach facility design and 3 plans

requiring Review and Approval under the existing Water License. On May

14, 2018 the Company received a letter from the Water Board stating

these plans, as revised, are sufficient in nature to require an

amendment to the license rather than being captured under the Review

and Approval process outlined in the existing license. The Company

believes all technical information required to satisfy the amendment

requirements has already been submitted and the Company is currently

preparing the amendment application, which will be submitted later this

week.

Importantly, the existing Water License remains in effect. Site

construction activities remain unaffected and the Company believes

there will be no interruption to the construction schedule as a result

of this directive.

About the Dublin Gulch Property

Victoria Gold's 100%-owned Dublin Gulch gold property is situated

in the central Yukon Territory, Canada, approximately 375 kilometers

north of the capital city of Whitehorse, and approximately 85

kilometers from the town of Mayo. The Property is accessible by road

year-round, and is located within Yukon Energy's electrical grid. The

Company has constructed and maintains a 210 person all-season camp at

the project site.

The Property covers an area of approximately 555 square

kilometers, and is the site of the Company's Eagle Gold Deposit. The

Eagle Gold Mine is expected to be Yukon's next operating gold mine and,

between the Eagle and Olive deposits, include Proven and Probable

Reserves of 2.7 million ounces of gold from 123 million tonnes of ore

with a grade of 0.67 grams of gold per tonne, as outlined in a National

Instrument 43-101 feasibility study. The NI 43-101 Mineral Resource for

the Eagle and Olive deposits has been estimated to host 191 million

tonnes averaging 0.65 grams of gold per tonne, containing 4.0 million

ounces of gold in the "Measured and Indicated" category, inclusive of

Proven and Probable Reserves, and a further 24 million tonnes averaging

0.61 grams of gold per tonne, containing 0.5 million ounces of gold in

the "Inferred" category.

Qualified Person

The technical content of this news release has been reviewed and

approved by Tony George, P.Eng., as the Qualified Person. For

additional information relating to the Property, refer to the technical

report entitled "NI 43-101 Feasibility Study Technical Report for the

Eagle Gold Project, Yukon Territory, Canada", with an effective date of

September 12, 2016, which is available on the Company's profile at

www.sedar.com.

Cautionary Language and Forward-Looking Statements

Neither the TSX Venture Exchange, nor its Regulation Services

Provider accepts responsibility for the adequacy or accuracy of this

release. This press release includes certain statements that may be

deemed "forward-looking statements". All statements in this discussion,

other than statements of historical facts, that address future

exploration drilling, exploration activities, anticipated metal

production, internal rate of return, estimated ore grades, commencement

of production estimates and projected exploration and capital

expenditures (including costs and other estimates upon which such

projections are based) and events or developments that the Company

expects, are forward-looking statements. Although the Company believes

the expectations expressed in such forward-looking statements are based

on reasonable assumptions, such statements are not guarantees of future

performance and actual results or developments may differ materially

from those in forward-looking statements. Factors that could cause

actual results to differ materially from those in forward-looking

statements include metal prices, exploration successes, continued

availability of capital and financing, and general economic, market or

business conditions. Accordingly, readers should not place undue

reliance on forward-looking statements.

TEL:  416-866-8800  John McConnell, President & CEO

Victoria Gold Corp

FAX:  416-866-8801

WEBSITE:  www.vitgoldcorp.com

____________________________________________________________

(c)2018 Market News Publishing Inc.  All rights reserved.

Toronto:(416)366-8881   Vancouver:(604)689-1101   Fax:(604)689-1106

#1814300006TS11814300698-05231320180524##