Source	MARKET NEWS
Date	05/24/2018
Time	05:26:32 AM

Company	 Victoria Gold Corp.
Title	Provides 
Eagle Development Update, Yukon Territo





    CDNX Symbol: VIT











Press Release





VICTORIA GOLD CORP ("VIT-V;VITFF-0")
- Provides Eagle Development Update, Yukon Territory

Victoria Gold Corp. "Victoria" or the "Company" is pleased to
provide a construction update for the Eagle Gold Mine Project (the
"Project"), Yukon Canada. Full construction commenced March 15, 2018
with completion and first gold pour scheduled for the second half of
2019.

"The successful construction program completed late in 2017
allowed us to hit the ground running and construction of the Eagle Gold
Mine is off to an outstanding start," stated John McConnell, President
& CEO. "I am pleased with the significant number of Yukon based
companies and Yukon First Nation partnered businesses that have already
been engaged for construction which has resulted in a high level of
local hiring. This is an important focus area for Victoria as we build
Yukon's next and largest ever gold mine."

Engineering

Significant ramp up of engineering activities occurred during
March and April with overall engineering now at approximately 65%
complete. Currently, engineering activities are focused on Issued For
Construction ("IFC") drawings for concrete site works, power
transmission and schedule driven deliverables based on fabrication and
equipment delivery schedules.

Procurement

Total Project commitments to date are nearly C$200 million with
C$55 million incurred cost.  The 2016 Feasibility Study construction
capital plus year one sustaining capital was estimated at C$411
million, and the revised construction capital estimate was finalized at
C$442 million. The decision to purchase all new, as opposed to used,
major mobile equipment (to improve operational efficiency and take
advantage of attractive pricing) as well as inflationary increases in
pricing across the Project were main drivers for this capital increase.
All major long lead items have been procured, materially reducing the
risk of schedule delays for construction completion toward first gold
pour. All primary mobile mining equipment is scheduled to arrive at
site in June 2018 with crushers to follow in the Fall of this year.

Site Construction

Major earthworks are well underway on site and are focused on the
crushing plant, gold recovery plant and heap leach facility
preparation. Concrete contracts have been awarded and casting of
foundations for the crushing and gold recovery facilities will start
this July. Camp expansion from 250 to full 450 bed capacity has been
on-going and is scheduled for completion by the end of this month.

Total on-site construction work to date exceeds 185,000 hours. A
strong health, safety and environmental program and culture have been
established at site as witnessed by no lost time accidents.

Recruitment

Victoria continues to recruit senior staff for the owner's team as
operational readiness planning develops. This month, the Company
welcomes staff to the environmental and site support team with a
continued focus on hiring Yukoners.

Permitting

Pursuant to the Company's Water License, Victoria is required to
submit a number of post licensing submissions for Review and Approval
as a condition of license. Earlier this year, the Company made
submission of the revised heap leach facility design and 3 plans
requiring Review and Approval under the existing Water License. On May
14, 2018 the Company received a letter from the Water Board stating
these plans, as revised, are sufficient in nature to require an
amendment to the license rather than being captured under the Review
and Approval process outlined in the existing license. The Company
believes all technical information required to satisfy the amendment
requirements has already been submitted and the Company is currently
preparing the amendment application, which will be submitted later this
week.

Importantly, the existing Water License remains in effect. Site
construction activities remain unaffected and the Company believes
there will be no interruption to the construction schedule as a result
of this directive.

About the Dublin Gulch Property

Victoria Gold's 100%-owned Dublin Gulch gold property is situated
in the central Yukon Territory, Canada, approximately 375 kilometers
north of the capital city of Whitehorse, and approximately 85
kilometers from the town of Mayo. The Property is accessible by road
year-round, and is located within Yukon Energy's electrical grid. The
Company has constructed and maintains a 210 person all-season camp at
the project site.

The Property covers an area of approximately 555 square
kilometers, and is the site of the Company's Eagle Gold Deposit. The
Eagle Gold Mine is expected to be Yukon's next operating gold mine and,
between the Eagle and Olive deposits, include Proven and Probable
Reserves of 2.7 million ounces of gold from 123 million tonnes of ore
with a grade of 0.67 grams of gold per tonne, as outlined in a National
Instrument 43-101 feasibility study. The NI 43-101 Mineral Resource for
the Eagle and Olive deposits has been estimated to host 191 million
tonnes averaging 0.65 grams of gold per tonne, containing 4.0 million
ounces of gold in the "Measured and Indicated" category, inclusive of
Proven and Probable Reserves, and a further 24 million tonnes averaging
0.61 grams of gold per tonne, containing 0.5 million ounces of gold in
the "Inferred" category.

Qualified Person

The technical content of this news release has been reviewed and
approved by Tony George, P.Eng., as the Qualified Person. For
additional information relating to the Property, refer to the technical
report entitled "NI 43-101 Feasibility Study Technical Report for the
Eagle Gold Project, Yukon Territory, Canada", with an effective date of
September 12, 2016, which is available on the Company's profile at
www.sedar.com.

Cautionary Language and Forward-Looking Statements

Neither the TSX Venture Exchange, nor its Regulation Services
Provider accepts responsibility for the adequacy or accuracy of this
release. This press release includes certain statements that may be
deemed "forward-looking statements". All statements in this discussion,
other than statements of historical facts, that address future
exploration drilling, exploration activities, anticipated metal
production, internal rate of return, estimated ore grades, commencement
of production estimates and projected exploration and capital
expenditures (including costs and other estimates upon which such
projections are based) and events or developments that the Company
expects, are forward-looking statements. Although the Company believes
the expectations expressed in such forward-looking statements are based
on reasonable assumptions, such statements are not guarantees of future
performance and actual results or developments may differ materially
from those in forward-looking statements. Factors that could cause
actual results to differ materially from those in forward-looking
statements include metal prices, exploration successes, continued
availability of capital and financing, and general economic, market or
business conditions. Accordingly, readers should not place undue
reliance on forward-looking statements.

TEL:  416-866-8800  John McConnell, President & CEO
Victoria Gold Corp
FAX:  416-866-8801
WEBSITE:  www.vitgoldcorp.com
____________________________________________________________
(c)2018 Market News Publishing Inc.  All rights reserved.
Toronto:(416)366-8881   Vancouver:(604)689-1101   Fax:(604)689-1106

1814300006TS11814300698-05231320180524