Source	MARKET NEWS

Date	05/29/2018

Time	07:06:15 AM

Company	 Melior Resources Inc.

Title	Reports On

Progress Toward Production At Its Goo

CDNX Symbol: MLR

Press Release

MELIOR RESOURCES INC ("MLR-V;CCJMF-0")

- Reports On Progress Toward Production At Its Goondicum Ilmenite

- Project

Melior Resources Inc. ("Melior" or the "Company") provided details

about construction and development progress at its Goondicum Ilmenite

Project.

Project Scope & Description

On 9 April 2018, Melior announced the commencement of work on the

Goondicum restart project having procured US$12.25 million (C$15.7

million1) of debt facilities. Work commenced shortly thereafter with

the restart program anticipated to take a total of six months to

complete preproduction activities followed by commissioning and first

production scheduled to begin in November 2018. A total of C$9.8

million is budgeted to be spent on restart activities2, including

working capital, in the six month preproduction period.

The primary capital activities in the preproduction period

include:

*  Repairs and maintenance from previous operational period

*  Procuring critical spares

*  Improving aspects of the previous process flowsheet

*  Installation of additional processing circuits

*  Construction of additional tailings storage capacity

*  Offsite infrastructure construction

Progress as at May 25, 2018

Site activity has started to build momentum as supplies and

equipment are ordered, admin and work procedures finalized, and

construction and key long term operational personnel are on-boarded.

The total project is budgeted to take 21,661 man-hours to

complete. As of May 25, 2018, 609 man-hours had been worked on the

project completing 1,700 hours of budgeted work for a saving of 1,100

hours to date.  The overall project is estimated to be 11% complete.

No safety or environmental incidents have been recorded to date.

Mark McCauley, CEO of Melior said, "We are off to a great start

completing the construction work at Goondicum and remain on schedule

and within budget.  We anticipate that our target of commencing

production in November will be realized.  Ilmenite prices continue to

be robust and market feedback suggests on-going strength as we approach

our start date."

For the purposes of project planning and management, work has been

divided into project specific areas on a functional basis. Capital

expenditure has been allocated to these areas as shown in Table 1

below. These figures include all labour, parts and equipment directly

required to complete the job.  Each of these individual tasks are

relatively straightforward as stand-alone activities however, as a

cumulative project, detailed planning and scheduling is required to

ensure everything runs smoothly and the project is delivered on time

and on budget.

The critical path items in the construction period are the

refurbishment and installation of the run-of-mine (ROM) feeder unit

which is being transported to the mine site from Western Australia and

the installation of the attritioning circuit and the spiral merge

projects which are both reliant on the timely delivery of long-lead

time items from third party vendors.

The construction work will be carried out using a combination of

Goondicum's own employees and contractors where appropriate with the

project overseen by Project Manager Alastair Bauer, Construction

Manager Gerry Finch and CFO Jonathan Mattiske.

Table 1: Project Budget Breakdown

//st

Budgeted Preproduction Activity   C$ '000   Impact on the Operation

Water pipeline lime treatment     243       Ensure longevity of project

plant                                       water pipeline

Run-of-Mine (ROM) feeder          1,096     Reduce opex and improve

availability

Spiral merge project              606       Improve recoveries and

availability

Screen oversize attritioning      256       Improve recoveries

circuit

WHIMS water and feed              456       Improve recoveries and

reconfiguration                             product quality

Ilmenite dephos circuit           766       Improve product quality

Drying circuit feed arrangement   288       Improve availability

Tailings dams                     1,195     Operating requirement

Mining contractor mobilisation    73        Operating requirement

Light vehicles                    194       Operating requirement

Identified site defects           496       Operating requirement

Critical spares                   479       Operating requirement

Port storage                      296       Operating requirement

Other capex items                 827       Operating requirement

Contingency                       388

Preproduction Capital Budget      7,660

Rehabilitation bond               583       Operating requirement

Working capital                   1,527     General & administration

Total Goondicum Preproduction     9,770

Budget

//et

The next project update will be provided in late July.

About Melior

Melior is the owner and operator of the Goondicum mine, a

past-producing ilmenite and apatite mine strategically located in

Queensland Australia. Further details on Melior and the Goondicum mine

can be found at www.meliorresources.com and regulatory filings are

available on SEDAR.

Melior is incorporated under the provisions of the Business

Corporations Act (British Columbia) and has a registered office in

Toronto, Ontario. Melior is classified as a Tier 1 Mining Issuer under

the policies of the TSX-V.

Forward Looking Statements Disclaimer

Statements made in this news release may be forward-looking and

therefore subject to various risks and uncertainties. Such statements

can typically be identified by terminology such as "may", "will",

"could", "should", "expect", "plan", "anticipate", "believe", "intend",

"possible", "continue", "objective" or other similar expressions

concerning matters that are not historical facts. Certain material

factors or assumptions are applied in making forward-looking statements

and actual results may differ materially from those expressed or

implied in such statements. Melior does not undertake to update any

forward-looking statements; such statements speak only as at the date

made.

Neither the TSX Venture Exchange nor its Regulation Services

Provider (as that term is defined in the policies of the TSX Venture

Exchange) accepts responsibility for the adequacy or accuracy of this

release.

1 USD:CDN = 0.78, AUD:CDN = 1.03

2 Excludes Melior general and administration costs

TEL:  +61 7 3233 6300  Mark McCauley, Chief Executive Officer

MELIOR RESOURCES INC.

EMAIL:  info@meliorresources.com

____________________________________________________________

(c)2018 Market News Publishing Inc.  All rights reserved.

Toronto:(416)366-8881   Vancouver:(604)689-1101   Fax:(604)689-1106

#1814800043TS11814801370-06595220180529##