Source	Marketwire

Date	10/30/2007

Time	05:49:10 AM

Company	 POWERTECH URANIUM CORP.

Title	Powertech Uranium Corp.: Centennial Project- Mine Permiting Update

CDNX Symbol: PWE

Press Release

NEWS RELEASE TRANSMITTED BY MARKETWIRE

FOR: Powertech Uranium Corp.

TSX VENTURE SYMBOL: PWE

FRANKFURT SYMBOL: P8A

October 30, 2007

Powertech Uranium Corp.: Centennial Project- Mine Permiting Update

VANCOUVER, BRITISH COLUMBIA--(Marketwire - Oct. 30, 2007) - POWERTECH URANIUM

CORP. (TSX VENTURE:PWE) (FRANKFURT:P8A) ("Powertech" or the "Company") is

pleased to announce that activities associated with its mine permit application

for the Centennial Project, in Weld County, Colorado are advancing on schedule.

Several major milestones have been completed to date, including:

- A network of 49 groundwater wells has been completed in the project area.

Some of these wells are being used to perform aquifer tests through October and

November 2007. This testing will characterize the hydrology of the mineral

bearing sands, as well as the stratigraphic units above and below the

mineralized sands. Based on the results of these tests, aquifer process and

restoration studies are scheduled to be initiated by November 15, 2007. Water

samples from these wells have been collected and will also be analyzed to

provide quarterly baseline water quality data for the project. Included in this

network of groundwater wells are 26 historical groundwater observation wells

completed in the 1980's. The State Engineer complimented Powertech on its

proactive measures to retrofit these wells into the current groundwater

monitoring program.

- The program of domestic well sampling is progressing as planned. Historical

analyses show that water used for domestic purposes have high nitrate and iron

mineral content. To date, no registered domestic water wells have been found to

be completed within the mineralized sand units.

- A conceptual three dimensional geologic site model has been completed. This

modeling demonstrates that the proposed in-situ recovery ("ISR") operation is

isolated from existing registered domestic wells.

- A surface water monitoring program consisting of 13 stations is in its third

month of operation and representative surface water impoundments have been

sampled.

- Terrestrial ecological surveys are underway and are scheduled to be completed

by December 31, 2007.

- Cultural resource studies continue. No significant findings have been

reported to date.

- Reclamation and radiological profile soil studies have been completed.

- The first of three radon flux samples have been obtained.

- Gamma radiation transect surveys are underway.

- High volume particulate samplers, as well as a meteorological tower, are

ready for installation pending approval from Weld County.

- A coring program was completed in July and August 2007. Samples of

mineralized core have been sent to Energy Labs in Casper, Wyoming for uranium

and metals analyses.

- Geotechnical analyses of core samples indicate the mineralized sands exhibit

high horizontal permeabilities, while extremely low vertical permeabilities are

found within confining clay units above and below the mineralized sands - ideal

conditions for ISR operations. Other mineralized core samples have been set

aside for column leach testing, which is scheduled to begin in late November

2007. The data from the column studies will be used to design production wells

fields and to support the aquifer restoration plan.

- The preparation of an application to the EPA for an Underground Injection

Control permit has been initiated.

George M. L. Robinson of R Squared, Inc., the prime contractor for the

completion of the mine permit and license application activities, states "We

are on schedule to complete our mine permit applications for submission in

2008. The federal, state and county regulatory agencies have been engaged and

no significant obstacles have been identified. The landowners have been

cooperative in the development of the baseline studies. State of the art

instrumentation and advanced analytical methods are being applied to

demonstrate and document that the project will not adversely impact human

health or the environment."

This news release has been reviewed and approved by Mr. Richard F. Clement,

President and CEO of Powertech, under whose direction the company's operations

are being carried out. Mr. Clement, P.Geo., MSc. is a Qualified Person as

defined by National Instrument 43-101.

About Powertech Uranium Corp.

Powertech Uranium Corp. is a Denver-based mineral exploration and development

company that holds the Dewey-Burdock Uranium Deposit in South Dakota, the

Centennial Project in Colorado and the Dewey Terrace and Aladdin Projects in

Wyoming. The company's key personnel have an aggregate of 200 years of

experience in the uranium industry throughout the United States, and have

permitted more than a dozen in-situ operations for production. For more

information, please visit http://www.powertechuranium.com/

POWERTECH URANIUM CORP.

Richard F. Clement Jr., President & CEO

Disclaimer for Forward-Looking Information

Certain statements in this release are forward-looking statements, which

reflect the expectations of management regarding the Company's Centennial

Project mine permitting and licensing activities and schedule. Forward-looking

statements consist of statements that are not purely historical, including any

statements regarding beliefs, plans, expectations or intentions regarding the

future. Such statements are subject to risks and uncertainties that may cause

actual results, performance or developments to differ materially from those

contained in the statements. No assurance can be given that any of the events

anticipated by the forward-looking statements will occur or, if they do occur,

what benefits the Company will obtain from them. These forward-looking

statements reflect management's current views and are based on certain

expectations, estimates and assumptions which may prove to be incorrect. A

number of risks and uncertainties could cause our actual results to differ

materially from those expressed or implied by the forward-looking statements,

including: (1) a downturn in general economic conditions in North America and

internationally, (2) the inherent uncertainties and speculative nature

associated with uranium exploration, (3) a decreased demand for uranium, (4)

any number of events or causes which may delay or cease exploration and

development of the Company's property interests, such as environmental

liabilities, weather, mechanical failures, safety concerns and labour problems;

(5) the risk that the Company does not execute its business plan, (6) inability

to retain key employees, (7) inability to finance operations and growth, (8)

inability to obtain all necessary environmental and regulatory approvals, (9)

an increase in the number of competitors with larger resources, and (10) other

factors beyond the Company's control. These forward-looking statements are made

as of the date of this news release and the Company assumes no obligation to

update these forward-looking statements, or to update the reasons why actual

results differed from those projected in the forward-looking statements.

Additional information about these and other assumptions, risks and

uncertainties are set out in the "Risks and Uncertainties" section in the

Company's MD&A filed with Canadian security regulators.

- 30 -

CONTACT INFO:

Powertech Uranium Corp.

Thomas A. Doyle

CFO, VP Finance

(604) 685-9181

Fax: (604) 685-9182

Email: info@powertechuranium.com

Website: www.powertechuranium.com

The TSX Venture Exchange has not reviewed and does not accept responsibility

for the adequacy or accuracy of the content of this News Release.

INDUSTRY: Manufacturing and Production - Mining and Metals

SUBJECT: MEX - MINING EXPLORATION UPDATE